## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Craft Foundry |  | 1 month | 2021-08-23 | 2021-09-25 | 2021-09-26
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-23 | 2021-08-26 | 3 days
1.2 | Finish webpage | 2021-08-27 | 2021-09-01 | 6 days
1.3 | Project Design | 2021-09-02 | 2021-09-02 | 2 days
2 | Coding
2.1 | Phase 1 | 2021-09-02 | 2021-09-06 | 6days
2.2 | Phase 2 | 2021-09-07 | 2021-09-13 | 7Days
2.3 | Additional Features
3 | Testing
3.1 | Phase 1 Testing | 2021-09-14 | 2021-09-14 | 1 day
3.2 | Modification /Any changes | 2021-09-15 | 2021-09-17 | 3days
3.3 | Phase 2 Testing | 2021-09-17 | 2021-09-18 | 2 day
3.4 | Modification /Any changes | 2021-09-19 | 2021-09-19 | 1day
3.5 | Final Testing | 2021-09-20 | 2021-09-20 | 1 day
4 | Documentation
4.1 | User Guide | 2021-09-21 | 2021-09-21 | 1 day
4.2 | Presentation | 2021-09-22 | 2021-09-22 | 1day

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Backend & front end
| Member Name | Rashmi Dongarkar
| PRN No | 210543181076
Description
2 | Role | Front end & Back end
| Member Name | Vaishnavi Patil
| PRN No | 210543181066
Description
3 | Role | Front end & Back end
| Member Name | Sayli Dhaygude
| PRN No | 210543181094
Description
4 | Role | Backend & front end
| Member Name | Akshy Phargade
| PRN No | 210543181094
Description